## Project X Action Plan
Project X Action Plan
Mindset Childrens Homes
Mobalisation
Project Manager |  |  | Date
Noel Beaumont (Director) |  |  | 2026-02-01
Goal
To launch and mobilize Mindset Childrens Home as a compassionate, self-sustaining model that delivers exceptional care, education, and opportunity to vulnerable children through dedicated resources, partnerships, and community support.
Phase 1: Discovery & Planning
Priority | Action Item | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
Medium | Identify Location For Childrens Home | Complete | 2026-02-02 | 2026-02-08 | 6 | Noel |  | 0 | Noel identified that Nottingham would not be the ideal location for a childrens home as the demand seems to be for supported accomidation. Loughbourough deemed the most appropriate area.
Medium | Identify Agent that supply properties with C2 planning permission | Complete | 2026-02-02 | 2026-02-08 | 6 | Arnold |  | 0 | Agent Identified: Lovemore. X2 Properties Identified
Medium | TOB to be agreed with Agent | Complete | 2026-02-02 | 2026-02-04 | 2 | Arnold |  | 3000 | TOB Agreed. Requirnent of DNA, Mindset only commit once a company is sourced. Payment of finders fee to be made to remove the property from the market, the deposit to the landlady will also have to be made. 5-7 year contract
Medium | Property viewing | Complete | 2026-02-02 | 2026-02-04 | 2 | Steven/Arnold |  | 0 | X2 properties viewed. 14 Pulteney & 389 New Ashby Road.
Medium | Directors to agree to proceed following viewings | Complete | 2026-02-04 | 2026-02-05 | 1 | All |  | 0 | Steven & Arnold attned the property on 05/02/2026. Meeting held with all directors who agreed to proceed based on the findings.
Medium | Initial requirments of additional works to be sent to the agent. | Complete | 2026-02-05 | 2026-02-05 | 0 | Steven |  | 0 | Email sent with requirments 05/02/2026
Medium | Estimated Costings to be produced showing 3 different models | Complete | 2026-02-05 | 2026-02-05 | 0 | Arnold |  | 0 | Shared with all directors
High | Meet to negotiate rental costs | Complete | 2026-02-05 | 2026-02-05 | 0 | Steven/Arnold |  | 0 | Rent negotiated down from £3500 to £2900, saving £7200 PA.
Low | Source planning documents | Complete | 2026-02-05 | 2026-02-05 | 0 | Steven |  | 0 | Sent to all directors
Low | 6 month rent to be paid as part of the rental agreement | Complete | 2026-02-16 | 2026-02-16 | 0 | Arnold |  | 20400 | Arnold completed and send info to all directors.
High | Set up Companies House with each director having 25% shares | Not Started | 2026-02-16 | 2026-02-23 | 7 | Clem |  | 0
Phase 2: Mobalisation
Priority | Action Item | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | Register a children’s social care service (SC1) | Not Started |  |  | 0 |  |  | 0
High | RI SC2 | Not Started |  |  | 0 |  |  | 0
High | Manager SC2 | Not Started |  |  | 0 |  |  | 0
High | Manager Health Decliration | Not Started |  |  | 0 |  |  | 0
High | Statement of Purpose | Not Started |  |  | 0 |  |  | 0
High | Local Area Risk Assessment | Not Started |  |  | 0 |  |  | 0
High | Business Plan | Not Started |  |  | 0 |  |  | 0
High | Planning Permission | Not Started |  |  | 0 |  |  | 0
High | Childrens Guide | Not Started |  |  | 0 |  |  | 0
High | Continuity/Contingency Plan | Not Started |  |  | 0 |  |  | 0
High | Policies (See Policy Index) | Not Started |  |  | 0 |  |  | 0
High | Workforce Development Plan | Not Started |  |  | 0 |  |  | 0
High | Training Matrix | Not Started |  |  | 0 |  |  | 0
High | Business Insurance | Not Started |  |  | 0 |  |  | 0
High | Appoint Regg 44 Inspector | Not Started |  |  | 0 |  |  | 0
High | Fire Risk Assessment (Independent) | Not Started |  |  | 0 |  |  | 0
High | Asbestos Check | Not Started |  |  | 0 |  |  | 0
High | Legionnaires Check | Not Started |  |  | 0 |  |  | 0
High | Ensure Planning Conditions are met (if any) | Not Started |  |  | 0 |  |  | 0
High | Job Posts | Not Started |  |  | 0 |  |  | 0
High | Emergency Fire Evacuation Procedure & Plan | Not Started |  |  | 0 |  |  | 0
High | Fire Door Certificates | Not Started |  |  | 0 |  |  | 0
High | Fire/Smoke/Carbon Monoxide Alarm Certificate | Not Started |  |  | 0 |  |  | 0
High | Action Plan following FRA | Not Started |  |  | 0 |  |  | 0
High | Notification to the police | Not Started |  |  | 0 |  |  | 0
High | Notification letter to the fire brigade | Not Started |  |  | 0 |  |  | 0
High | Food Premises Certificate | Not Started |  |  | 0 |  |  | 0
High | Gas Safety Certificate | Not Started |  |  | 0 |  |  | 0
High | Eletrical Certificate | Not Started |  |  | 0 |  |  | 0
High | PAT Test Certificate | Not Started |  |  | 0 |  |  | 0
High | C2 Certificate | Not Started |  |  | 0 |  |  | 0
High | House Risk Assessment | Not Started |  |  | 0 |  |  | 0
High | Rota Management | Not Started |  |  | 0 |  |  | 0
High | Staff Induction Documents | Not Started |  |  | 0 |  |  | 0
High | Employee Handbook | Not Started |  |  | 0 |  |  | 0
High | External CCTV | Not Started |  |  | 0 |  |  | 0
High | Window Restrictors | Not Started |  |  | 0 |  |  | 0
High | Thumb Locks on doors | Not Started |  |  | 0 |  |  | 0
High | Internet | Not Started |  |  | 0 |  |  | 0
High | Staff Phones | Not Started |  |  | 0 |  |  | 0
High | Staff laptop x2 | Not Started |  |  | 0 |  |  | 0
High | Staff Tablet for the community x1 | Not Started |  |  | 0 |  |  | 0
High | Car Purchase | Not Started |  |  | 0 |  |  | 0
High | Car insurance & MOT | Not Started |  |  | 0 |  |  | 0
High | Sign up to Lief | Not Started |  |  | 0 |  |  | 0
High | Mock Fit Persons Interview | Not Started |  |  | 0 |  |  | 0
High | Generic Risk Assessment | Not Started |  |  | 0 |  |  | 0
High | Pet Risk Assessment | Not Started |  |  | 0 |  |  | 0
High | Health & Enviroment Risk Assessment | Not Started |  |  | 0 |  |  | 0
High | Employee Handbook | Not Started |  |  | 0 |  |  | 0
High | Aquire TV License | Not Started |  |  | 0 |  |  | 0
High | Agree Chilf Budget | Not Started |  |  | 0 |  |  | 0
High | Implement Chck Chore & Audit Section on Lief | Not Started |  |  | 0 |  |  | 0
Phase 3: Recruitment, Training & Development
Priority | Action Item | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
Low |  | Not Started |  |  | 0 |  |  | 0
Medium |  | Not Started |  |  | 0 |  |  | 0
High |  | Not Started |  |  | 0 |  |  | 0
Low |  | Not Started |  |  | 0 |  |  | 0
Medium |  | Not Started |  |  | 0 |  |  | 0
High |  | Not Started |  |  | 0 |  |  | 0

## Dropdown Key - Do Not Delete (hidden)
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress
On Hold